## Sheet1
Tasks | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27
Pre-internship setup
Familiarization with ROS2.0
+ Install ROS2.0 on Windows or Ubuntu
+ Import LD robot 3D model
+ Jog LD robot (teleop)
Visited ARTC to find out more about membership and training
- Membership rates for projects - Participation in pre-competitive shared projects advancing ROS for industry-specific applications - Full membership: Voting of priorities for shared projects - Up to 3 free ROS trainings per year (2 for associate member) - Up to 3 free seats for the Annual Workshop (2 for associate member) - Full membership gets automatic associate tier access to the Europe and Americas regions as well – you could join their conference, send staff in these regions to their training, and participate in their pre-competitive projects SGD7000/year for associate membership, pro-rated, 4k cash Architecture advice is SGD125/hour: 8h*2days*10weeks = 160h = SGD20k
Engagement roadmap
ROS 1.0 training | [10 empty] | x
Mentor intern when writing ROS layer | [10 empty] | x | x
P&G pj using LD250 to move drums
CHART engagement?
Start of internship
Install Ubuntu ROS1.0 and Windows ROS 2.0 on T440 laptop
Introduce existing ROS packages with Omron robots for exploration
ROS-I Developer's Training 24-27/9 - Basic+Advanced SGD950each
ROS for LD robots
Understand how LD robot works (attach to Rajaram)
Learn ARCL commands
Choose ARCL functions to create ROS publishers
Able to write script to move LD robot a relative distance and to a pre-taught goal
Documentation and upload to GTKS (how can NSCs/customers use it)
ROS for TM robots (TM5-700)
Try TM ROS1.0 package available online
https://github.com/kentsai0319/techman_robot
Run Mobile Manipulator with ROS
ROS for Sysmac
Learn to write PLC programs on Sysmac Studio
Write FB to talk to ROS packages
Perform pick and place with Viper
Documentation and upload to GTKS (how can NSCs/customers use it)
Drone with LD robots
Try autonomous navigation of drone with ROS
Integrate LD navigation with drone action
Test in lab
Documentation and upload to GTKS (how can NSCs/customers use it)
ROS links
https://index.ros.org/doc/ros2/
https://index.ros.org/doc/ros2/Tutorials/
https://index.ros.org/doc/ros2/Installation/Dashing/
http://wiki.ros.org/navigation/Tutorials/RobotSetup
https://github.com/cse481wi18/cse481wi18/wiki/Lab-15%3A-Driving-with-odometry

## Plan - Matthew
|  |  | October |  |  | November | [20 empty] | December | [21 empty] | January | [22 empty] | February
|  |  | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7
| Task | Output | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
LD Robot
1 | Draft out ROS diagram with nodes, topics for ARCL 'status' command | Diagram of package with nodes and topics ROS package with correct structure and files | bar: October 29
2 | Create package with publishers for ARCL 'status' command | One node that publishes 5 topics - Status; BatteryVoltage; Location; LocalizationScore; Temperature | bar: October 30
3 | Split ARCL commands into topics, services or actions | bar: October 31
4 | Use namespaces to publish topics for multiple robots | Use lauch files | bar: November 1
5 | Write publishers for 5 ARCL commands | May need custom messages | bar: November 1 to November 4
6 | Write publishers for remaining ARCL commands | May need custom messages | bar: November 4
7 | Write actions for 3 ARCL commands | e.g. patrol; dock | bar: November 5 to November 6
8 | Write actions for remaining 7 ARCL commands | bar: November 6 to November 7
9 | Write services for 10 ARCL commands | May need custom services | bar: November 7 to November 8
10 | Write services for 20 ARCL commands | May need custom services | bar: November 8 to November 12
11 | Write services for 20 ARCL commands | May need custom services | bar: November 12 to November 14
12 | Write services for remaining ARCL commands | May need custom services | bar: November 14 to November 15
13 | Functional tests of ROS packages on actual robot | Moving to goal; dock; patrol; say; move relative distance | bar: November 18 to November 20
14 | Integration tests of ROS packages on actual robots | Move two robots between multiple goals | bar: November 20 to November 22
15 | Document how to use code using inline comments and README | Instructions on how to install/modify code; limitations of code; what needs to be done on Mobile Planner | bar: November 25 to November 29
16 | Get Rajaram to use ROS packages from Github | Goal: use documentations to write ROS code to move LD robot | bar: November 29
17 | Documentation | bar: December 2
TM Robot
MoMa

## ARCL commands
| ARCL command [ARCL Reference Guide, 18448-000 Rev A, Updated: 1/19/2017] | Robot or EM | Grouping | Notes | TOPIC | SERVICE | ACTION
1 | analogInputList Command 63 | Robot | Hardware | Lists the named analog inputs
2 | analogInputQueryRaw Command 64 | Robot | Hardware | Queries the state of an analog input by raw
3 | analogInputQueryVoltage Command 65 | Robot | Hardware | Queries the voltage of an analog input
4 | applicationFaultClear Command 66 | Robot | Utilities | Clears a named application fault
5 | applicationFaultQuery Command 67 | Robot | Utilities | Gets the list of any application faults currently triggered
6 | applicationFaultSet Command 69 | Robot | Utilities | Sets an application fault
7 | arclSendText Command 71 | Both | Utilities | Sends the given message to all ARCL clients
8 | configAdd Command 72 | Both | Utilities | Enter sections and related configuration parameter keywords and values to the configuration list
9 | configParse Command 74 | Both | Utilities | Sends the configuration parameters to ARAM, which implements the configuration changes
10 | configStart Command 76 | Both | Hardware | Initialize a configuration list, similar to creating a task list. The configStart command overwrites any previous list.
11 | connectOutgoing Command 78 | Both | Hardware | Connects (or reconnects) a socket to the specified outside server
12 | createInfo Command 79 | Robot | Utilities | Creates a piece of information
13 | dock Command 81 | Robot | Motion | Sends the robot to the dock
14 | doTask Command 82 | Robot | Motion | Performs a single task.
15 | doTaskInstant Command 84 | Robot | Hardware | Performs an instant task - see list in Mobile Planner
16 | echo Command 86 | Both | Utilities | Enables/disables echo, or returns the current echo state
17 | enableMotors Command 87 | Robot | Hardware | Enables the robot motors, if the robot was not E-stopped
18 | executeMacro Command 88 | Robot | Utilities | Executes the specified macro
19 | extIOAdd Command (shortcut: eda) 90 | Both | Hardware | Creates a new external I/O set. This is a bank of inputs and outputs with a friendly name
20 | extIODump Command (shortcut: edd) 92 | Both | Hardware | Debug function used to dump the values of all the external I/Os. Only on if MP->Debug->DebugExternalIO is checked
21 | extIODumpLocal Command (shortcut: eddl) 94 | Robot | Hardware | Debug function used to dump the values of all the external I/Os. Only on if MP->Debug->DebugExternalIO is checked
22 | extIOInputUpdate Command (shortcut: ediu) 96 | Both | Hardware | Updates the values of the inputs for a specified external I/O set
23 | extIOInputUpdateBit Command (shortcut: edib) 98 | Both | Hardware | Updates a specific bit in the external digital input set.
24 | extIOInputUpdateByte Command (shortcut: edi8) 100 | Both | Hardware | Updates a specific byte in the named external digital output set.
25 | extIOOutputUpdate Command (shortcut: edou) 102 | Both | Hardware | Updates the values of the outputs for an external I/O set. Meant to be used by the external device handling the real I/Os to update the output settings
26 | extIOOutputUpdateBit Command (shortcut: edob) 104 | Both | Hardware | Updates a specific bit in the external I/O set. Meant to be used by the external device handling the real I/Os to update the output settings.
27 | extIOOutputUpdateByte Command (shortcut: edo8) 106 | Both | Hardware | Updates a specific byte in the named external digital output device
28 | extIORemove Command (shortcut: edr) 108 | Both | Hardware | Removes an external I/O set
29 | faultsGet Command 109 | Robot | Utilities | Gets the list of any faults currently triggered
30 | getConfigSectionInfo Command 111 | Both | Hardware | Displays details about the configuration parameters in a specified section
31 | getConfigSectionList Command 113 | Both | Hardware | Displays the list of sections enabled in the ARAM configuration parameters
32 | getConfigSectionValues Command 115 | Both | Hardware | Displays the current parameter values for the specified section
33 | getDataStoreFieldInfo Command (shortcut: dsfi) 117 | Both | Utilities | Gets information on a field in the DataStore
34 | getDataStoreFieldList Command (shortcut: dsfl) 119 | Both | Utilities | Gets the list of field names in the DataStore
35 | getDataStoreFieldValues Command (shortcut: dsfv) 121 | Both | Utilities | Gets the values of a field in the DataStore
36 | getDataStoreGroupInfo Command (shortcut: dsgi) 122 | Both | Utilities | Gets the info on a group in the DataStore
37 | getDataStoreGroupList Command (shortcut: dsgl) 124 | Both | Utilities | Gets the list of groups in the DataStore
38 | getDataStoreGroupValues Command (shortcut: dsgv) 125 | Both | Utilities | Gets the values of a group in the DataStore
39 | getDataStoreTripGroupList Command (shortcut: dstgl) 126 | Both | Utilities | Returns the list of groups in the DataStore that contain trip information
40 | getDateTime Command 127 | EM | Utilities | Returns the system date and time
41 | getGoals Command 128 | Both | Utilities | Returns a list of goal names found in the current map
42 | getInfo Command 129 | Robot | Utilities | Returns the string associated with the information name
43 | getInfoList Command 131 | Robot | Utilities | Returns the list of information names
44 | getMacros Command 133 | Robot | Utilities | Displays a list of macros found in the current map
45 | getRoutes Command 135 | Robot | Utilities | Displays the list of route names found on the current map
goTo Command
46 | help Command 136 | Both | Utilities | Provides a list and brief description of available ARCL commands.
47 | inputList Command 137 | Robot | Hardware | Lists the named digital inputs
48 | inputQuery Command 139 | Robot | Hardware | Queries the state of a named input
49 | log Command 140 | Both | Utilities | Logs the message to the normal log file
50 | mapObjectInfo Command 142 | Both | Utilities | Gets the information about a named map object
51 | mapObjectList Command 144 | Both | Utilities | Gets the names of map objects of a given type
52 | mapObjectTypeInfo Command 146 | Both | Utilities | Gets detailed information about a particular type of map object
53 | mapObjectTypeList Command 148 | Both | Utilities | Gets a list of the types of map objects in the map
54 | newConfigParam Command 150 | Both | Utilities | Adds a custom parameter to ARAM’s configuration, which can then be managed through ARCL or MobilePlanner
55 | newConfigSectionComment Command 152 | Both | Utilities | Adds a comment to a section
56 | odometer Command 154 | Robot | Hardware | Shows the robot trip odometer readings
57 | odometerReset Command 155 | Robot | Hardware | Resets the robot trip odometer
58 | oneLineStatus Command 156 | Robot | Utilities | Shows the status of the robot on one line of text
59 | outputList Command 158 | Robot | Hardware | Lists the named digital outputs
60 | outputOff Command 160 | Robot | Hardware | Turns off the named digital output
61 | outputOn Command 161 | Robot | Hardware | Turns on the named digital output
62 | outputQuery Command 162 | Robot | Hardware | Queries the state of a named output
63 | patrol Command 164 | Robot | Motion | Initiates continuous patrol of the named route
64 | patrolOnce Command 166 | Robot | Motion | Patrol the named route one time
65 | patrolResume Command 168 | Robot | Motion | Continue navigating the current route.
66 | payloadQuery Command (shortcut: pq) 170 | EM | Hardware | Queries the payload for a specified robot, a specified robot and slot, or all connected robots that have a payload configured
67 | payloadQueryLocal Command (shortcut: pql) 173 | Robot | Hardware | Queries the payload for the robot and specified slot
68 | payloadRemove Command (shortcut: pr) 175 | Robot | Hardware | Empties the specified payload slot on the robot
69 | payloadSet Command (shortcut: ps) 177 | Robot | Hardware | Defines a payload slot on this robot
70 | payloadSlotCount Command (shortcut: psc) 179 | EM | Hardware | Displays the slot count on a specific robot or on all robots
71 | payloadSlotCountLocal Command (shortcut: pscl) 181 | Robot | Hardware | Displays a slot count on this robot
72 | play Command 182 | Robot | Hardware | Plays a .wav sound file on the robot
73 | popupSimple Command 184 | Both | Utilities | Display a popup message in the MobilePlanner software
74 | queryDockStatus Command 186 | Robot | Hardware | Gets the docking/charging status
75 | queryFaults Command (shortcut: qf) 187 | EM | Hardware | Displays the faults associated with the specified robot
76 | queryMotors Command 190 | Robot | Hardware | Gets the state of the robot motors
77 | queueCancel Command (shortcut: qc) 192 | EM | Motion | Cancels a queued request for a robot by type or value
78 | queueCancelLocal Command (shortcut: qcl) 195 | Robot | Motion | Cancels a queued request for a robot by type or value
79 | queueDropoff Command (shortcut: qd) 198 | Robot | Motion | Queues the robot to the dropoff goal
80 | queueModify Command (shortcut: qmod) 201 | EM | Motion | Allows modification of goal and priority for job segments
81 | queueModifyLocal Command (shortcut: qmodl) 207 | Robot | Motion | Allows modification of goal and priority for job segments
82 | queueMulti Command (shortcut: qm) 212 | EM | Motion | Queues the robot for multiple pickups and dropoffs at multiple goals
83 | queuePickup Command (shortcut: qp) 216 | EM | Motion | Calls any available robot for a pick up request
84 | queuePickupDropoff Command (shortcut: qpd) 219 | EM | Motion | Queues a pick-up and drop-off request for any available robot.
85 | queueQuery Command (shortcut: qq) 224 | EM | Motion | Shows the job status of the queue by type or value
86 | queueQueryLocal Command (shortcut: qql) 227 | Robot | Motion | Shows the job status of the robot queue by type or value
87 | queueShow Command (shortcut: qs) 230 | EM | Motion | Shows the status of the last 11 jobs in the queue, including any jobs assigned to the robots and the status of each job
88 | queueShowCompleted Command (shortcut: qsc) 232 | EM | Motion | Shows the jobs in the queue with a status of Completed
89 | queueShowRobot Command (shortcut: qsr) 234 | EM | Hardware | Shows the status and substatus of all robots (or, optionally, a specific robot) connected to the Enterprise Manager
90 | queueShowRobotLocal Command (shortcut: qsrl) 236 | Robot | Hardware | displays the status of the robot
91 | quit Command 237 | Both | Utilities | Closes the connection to the server.
92 | say Command 238 | Robot | Utilities | Speak a text string through the robot audio output
93 | shutdown Command 239 | Robot | Utilities | Shuts down the robot
94 | status Command 240 | Robot | Utilities | Returns the operational state of the robot
95 | stop Command 242 | Robot | Motion | Stops the current robot motion
96 | tripReset Command (shortcut: tr) 243 | Both | Utilities | Resets the trip values in the DataStore.
97 | undock Command 245 | Robot | Motion | Undocks the robot
98 | updateInfo Command 246 | Robot | Utilities | Updates the value for an existing piece of information.
99 | waitTaskCancel Command 248 | Robot | Utilities | Cancels a wait task if one is active
100 | waitTaskState Command 250 | Robot | Utilities | Displays the status of the wait task
[5 empty] | #NAME? | #NAME? | #NAME?
| addCustomCommand |  |  | Adds a custom command that'll send a message out ARCL when called
| addCustomStringCommand |  |  | Adds a custom string command that'll send a message out ARCL when called
| applicationBlockDrivingClear |  |  | Clears an application blockDriving [abdc]
| applicationBlockDrivingSet |  |  | Sets an application blockDriving [abds]
| centralServer |  |  | Gets information about the central server connection
| executeMacroTemplate |  |  | executes a specified macro template with the given parameters
| freeMotors |  |  | Frees the motors (note that the brakes are not enabled, so this is Unsafe and should only be used by trained personnel in careful conditions)
| getMacroTemplates |  |  | gets a list of macro templates in the map (for use with executeMacroTemplates)
| getPoseEncoder |  |  | Gets the encoder pose of the robot
| go |  |  | Stops the robot from any wait it is doing then resume patrolling or makes The robot idle 2 minutes so that it will resume doing queued jobs (with the right parameters). See also stay.
| goalDistanceRemaining |  |  | Gets the distance remaining to robots goals
| goalDistanceRemainingLocal |  |  | Gets the distance remaining to this robot's goal
| Localizes to a given goal [lag] |  |  | localizeAtGoal
| MARCOverrideAnalog |  |  | Usage: <command> <0-15> <flags as int or hex (16 bits)> This overrides the normal analog from MARC for purposes of testing. Hex will work. [moa]
| MARCOverrideAnalogOut |  |  | Usage: <command> <0-3> <flags as int or hex (16 bits)> This overrides the normal analog output from MARC for purposes of testing. Hex will work. [moo]
| MARCOverridePowerStatus1 |  |  | Usage: <command> <flags as int or hex (8 bits)> This overrides the normal flags from MARC for purposes of testing. Hex will work. [mops1]
| MARCOverridePowerStatus2 |  |  | Usage: <command> <flags as int or hex (8 bits)> This overrides the normal flags from MARC for purposes of testing. Hex will work. [mops2]
| modeLock |  |  | Locks the current mode
| modeQuery |  |  | Queries the current mode and it's lock status
| modeUnlock |  |  | Unlocks the current mode
| newConfigParamEnd |  |  | Finishes adding multiple params to the config. Must be paired with a NewConfigParamStart.
| newConfigParamStart |  |  | Starts adding multiple params to the config. Optional. If specified, Must be followed by a newConfigParamEnd.
| newConfigSectionComment |  |  | Adds a comment to a section (shows up in MP)
| queueCancelMultiSegment |  |  | Cancels a multi goal job segment by id [qcms]
| waitTaskFail |  |  | Fails the wait task (if it's active)
| waitTaskState |  |  | Gets the state of the wait task

## Test Plan
Test Objective | Precondition | Steps | Test data | Expected results | Post-condition | Pass or Fail
Move robot to mulitple Goals with ros | Goals have to be set In mobile planner | Roslauch om_aiv_navigation robot1.py rosrun om_aiv_navigation test.py |  | robot moves to goal 1 Then goal 4
Get status of 2 robots At the same time | robots ips have to be Set in the launch file |  |  |  | the launch files runs the services server with different names as set in the service client file Rospy.wait forservice due to launching 2 of the Same service servers for robot1 and robot2 each. So the client file keep waiting for the service with The specific name but the service which run is of A different name.
Test topic applicationFaultQuery On actual robot. | robot ip have to be Set when launching launch File as command line arg | 1. Open 3 terminal windows 2. In one terminal run command: “roscore” 3. In second terminal window, run command: roslaunch om_aiv_util test_roslaunch.launch ip:=168.3.201.122 (ip address is unique to each robot) 4. In third terminal windows, run command: rostopic echo /ldarcl_ApplicationFaultQuery to suscribe to topic 5. Ctrl C in third terminal to stop suscribing to topic. repeat step 4 and suscribe to required topic. A list of topics can be viewed using rostopic list. |  | In third terminal windows, you should see data: "ApplicationFaultQuery: <fault status> where the <fault status> is the fault. | In third terminal window data recieved is : data: "ApplicationFaultQuery: No Faults" | Pass on 3 Dec 2019
Test topic faultsGet On actual robot. |  |  |  | In third terminal windows, you should see data: "FaultsGet: <fault status>" where the <fault status> is the fault. | data: "FaultsGet: No faults" | Pass on 3 Dec
Test topic getDateTime On actual robot. |  |  |  | In third terminal windows, you should see data: data: "<date and time> where the <date and time> is the date and time | data: "DateTime: 12/03/2019 05:03:04" | Pass on 3 Dec
Test topic odometer On actual robot. |  |  |  | In third terminal windows, you should see data: "<odometer> where <odometer> odometer values | data: "Odometer: 280 mm 369 deg 68978 sec" | Pass on 3 Dec
Test topic oneLineStatus On actual robot. |  |  |  | In third terminal windows, you should see data: "<oneLineStatus> where <oneLineStatus> is the status of the robot on one line of text | data: "Status: DockingState: Docked ForcedState: Unforced ChargeState: Float StateOfCharge:\ \ 98.5 Location: 640 27815 180 Temperature: 36" | Pass on 3 Dec
Test topic queryDockStatus On actual robot. |  |  |  | In third terminal windows, you should see data: "<dockStatus> where <dockStatus> is the docking/charging status | data: "DockingState: Docked ForcedState: Unforced ChargeState: Float" | Pass on 3 Dec
Test topic queryMotors On actual robot. |  |  |  | In third terminal windows, you should see data: "<MotorStatus> where <MotorStatus> is state of the motors | data: "EStop relieved but motors still disabled" | Pass on 3 Dec
Test topic queueShowRobotLocal On actual robot. |  |  |  | In third terminal windows, you should see data: "<status> where <status> is status of the robot | data: "QueueRobot: \"Robot122\" UnAvailable Interrupted \"\"" | Pass on 3 Dec
Test topic waitTaskState On actual robot. |  |  |  | In third terminal windows, you should see data: "<waitTaskState> where <waitTaskState> is the status of the wait task | data: "WaitState: Not waiting" | Pass on 3 Dec
Test 20 getInfo topics On actual robot. |  |  |  | In third terminal windows, you should see data: "<info> where <info> is the string associated with the information name | for example rostopic echo /ldarcl_getInfo_Idle: data: 67572 | Pass on 3 Dec
Test 6 status topics On actual robot. |  |  |  | In third terminal windows, you should see data: "<status> where <status> is the operational state of the robot | for example rostopic echo /ldarcl_status_temperature: data: 36.0 | Pass on 3 Dec
Pass on 3 Dec
Test analogInputList service on actual robot. | robot ip have to be Set when launching launch File as command line arg | 1. Open 3 terminal windows 2. In one terminal run command: “roscore” 3. In second terminal window, run command: roslaunch om_aiv_util test_roslaunch.launch ip:=168.3.201.122 (ip address is unique to each robot) 4. In third terminal windows, run command: rosrun om_aiv_util analogInputList_client.py 5. repeat step 4 for other services and input command line arguments if required |  | In third terminal window, you should see the named analog inputs | running command ['AnalogInputListHelper: List format is: <minVoltage> <maxVoltage> <maxRaw> <name>', 'AnalogInputListHelper: The data returned by analogInputQueryVoltage is a voltage as a double between <minVoltage> and <maxVoltage>', 'AnalogInputListHelper: The data returned by analogInputQueryRaw is an int called <rawValue>', "AnalogInputListHelper: To get <rawValue> to voltage do '<minVoltage> + (<maxVoltage> - <minVoltage>) * <rawValue> / <maxRaw>", 'End of AnalogInputList'] | Pass on 3 Dec
Test analogInputQueryRaw service on actual robot. |  |  |  | In third terminal window, the state of an analog input by raw is shown | ['name'] running command CommandError: analogInputQueryRaw name CommandErrorDescription: Must give device to query | Pass on 3 Dec
Test analogInputQueryVoltage service on actual robot. |  |  |  | In third terminal window, the voltage of an analog input is shown | running command CommandError: analogInputQueryVoltage NAME CommandErrorDescription: Must give device to query | Pass on 3 Dec
Test applicationFaultClear service on actual robot. (application fault have to be set first) |  |  |  | In third terminal window, it should show that the named application fault is cleared | running command FaultCleared: Fault_Driving_Critical_Application fault "test" "test" true true true false false ApplicationFaultClear cleared fault RobotFaultCleared: "Robot122" Fault_Driving_Critical_Application fault "test" "test" true true true false false | Pass on 3 Dec
Test applicationFaultSet service on actual robot. |  |  |  | In third terminal window, it should show that the application fault is set | running command ApplicationFaultSet set fault Fault: Fault_Application fault "test" "test" false false true false false | Pass on 3 Dec
Test arclSendText service on actual robot. |  |  |  | In third terminal window, it should show that the given message to all ARCL clients | running command test | Pass on 3 Dec
Test configAdd service on actual robot. (a new config has to be started first) |  |  |  | In third terminal window, it should show that the parameter keywords and values is added to the configuration list | Running command Added 'test test' to the config | Pass on 3 Dec
Test configParse service on actual robot. |  |  |  | In third terminal window, it should show that the configuration parameters have will be parsed | running command Will parse config | Pass on 3 Dec
Test configStart service on actual robot. |  |  |  | In third terminal window, it should show that the config is starting | running command New config starting | Pass on 3 Dec
Test connectOutgoing service on actual robot. |  |  |  | In third terminal window, it should show the socket connected to the ip address and port specified | running command Outgoing socket connected to 168.3.201.122 7171 | Pass on 3 Dec
Test createInfo service on actual robot. |  |  |  | In third terminal window, it should show that info has been created | Created info for test | Pass on 3 Dec
Test doTaskInstant service on actual robot. |  |  |  | In third terminal window, it should show that the instant task has been run | running command test Completed doing instant task ARCLSendText test | Pass on 3 Dec
Test echo service on actual robot. |  |  |  | In third terminal window, it should show echo status | running command Echo is off. | Pass on 3 Dec
Test enableMotors service on actual robot. |  |  |  | In third terminal window, it should show that motors have been enabled or why motors could not be enabled | running command EStop pressed cannot enable motors | Pass on 3 Dec
Test extIOAdd service on actual robot. |  |  |  | In third terminal window, it should show that new external I/O set has been created | running command extIOAdd: name added with 1 input(s) and 1 output(s) | Pass on 3 Dec
Test extIODump service on actual robot. |  |  | No command line arguments required | In third terminal window, it should show that the values of all the external I/Os have been dumped | Unknown command extIODump | failed on 4 dec. Command unknown
Test extIODumpLocal service on actual robot. |  |  | No command line arguments required | In third terminal window, it should show that the values of all the external I/Os have been dumped | Unknown command extIODumpLocal | failed on 4 dec. Command unknown
Test extIOInputUpdate service on actual robot. |  |  | name 2 | In third terminal window, it should show that the values of the inputs for a specified external I/O set has been updated | extIOInputUpdate: input name updated with 0x2 from 2 | passed on 4 dec 10:07am
Test extIOInputUpdateBit service on actual robot. |  |  | name 1 0 | In third terminal window, it should show that a specific bit in the external digital input set has been updated | extIOInputUpdateBit: input name updated with 0 at bit 1 to 0x2 | passed on 4 dec 10:14am
Test extIOInputUpdateByte service on actual robot. |  |  | name 1 1 | In third terminal window, it should show that a specific byte in the named external digital output set has been updated | extIOInputUpdateByte: input name updated with 0x1 at byte 1 to 0x1 | passed on 4 dec 10:16am
Test extIOOutputUpdate service on actual robot. |  |  | name 2 | In third terminal window, it should show that the values of the outputs for an external I/O set has been updated | extIOOutputUpdate: output name updated with 0x02 from 2 | passed on 4 dec 10:19am
Test extIOOutputUpdateBit service on actual robot. |  |  | name 1 0 | In third terminal window, it should show that a specific bit in the external I/O set has been updated | extIOOutputUpdateBit: output name updated with 0 at bit 1 to 0x02 | passed on 4 dec 10:23am
Test extIOOutputUpdateByte service on actual robot. |  |  | name 1 1 | In third terminal window, it should show that a specific byte in the named external digital output device has been updated | extIOOutputUpdateByte: output name updated with 0x0 at byte 1 to 0x00 | passed on 4 dec 10:27am
Test extIORemove service on actual robot. |  |  | name | In third terminal window, it should show that an external I/O set has been removed | extIORemove: name removed | passed on 4 dec 10:29am
Test getConfigSectionInfo service on actual robot. |  |  | sonar | In third terminal window, it should display details about the configuration parameters in a specified section | GetConfigSectionParamInfo: ...................................................................................................................................................................(a lot of data) EndOfGetConfigSectionInfo | passed on 4 dec 10:32am
Test getConfigSectionList service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should display the list of sections enabled in the ARAM configuration parameters | GetConfigSectionList:...........................................................................................................................................................................(list of sections) EndOfGetConfigSectionList | passed on 4 dec 10:35am
Test getConfigSectionValues service on actual robot. |  |  | sonar | In third terminal window, it should display the current parameter values for the specified section | GetConfigSectionValue: ............................................................................................................................(current parameter values for sonar section) EndOfGetConfigSectionValues | passed on 4 dec 10:37am
Test getDataStoreFieldInfo service on actual robot. |  |  | robots | In third terminal window, it should display the information on a field in the DataStore | GetDataStoreFieldInfo: Long long Robots Advanced 0 9223372036854775807 "Number of robots currently connected to EM (includes Available, UnAvailable, InProgress states)" "" "" EndOfGetDataStoreFieldInfo | passed on 4 dec 10:42am
Test getDataStoreFieldList service on actual robot. |  |  | no command line arg required | In third terminal window, it should display the list of field names in the DataStore | GetDataStoreFieldList: ................................................................................................................................................(list of field names in DataStore) EndOfGetDataStoreFieldList | passed on 4 dec 10:56am
Test getDataStoreFieldValues service on actual robot. |  |  | robots | In third terminal window, it should display the values of a field in the DataStore | DockingState: Undocking ForcedState: Unforced ChargeState: Overcharge DockingState: Undocking ForcedState: Unforced ChargeState: Float GetDataStoreFieldValues: Robots 1 EndOfGetDataStoreFieldValues | passed on 4 dec 11:05am
Test getDataStoreGroupInfo service on actual robot. |  |  | system | In third terminal window, it should display the info on a group in the DataStore | GetDataStoreGroupInfo: "Information about the system" "System" GetDataStoreGroupInfo: String RobotIP Advanced None None "IP address of the robot" "" "" GetDataStoreGroupInfo: String Odometer(KM) Advanced None None "Distance driven by robot (km)" "" "" GetDataStoreGroupInfo: String OdometerKM_MM Advanced None None "Distance driven by robot (km, mm)" "" "" GetDataStoreGroupInfo: String HourMeter Advanced None None "Time driven by robot (hours)" "" "" GetDataStoreGroupInfo: Int Idle Advanced -2147483648 2147483647 "(secs)" "" "" EndOfGetDataStoreGroupInfo | passed on 4 dec 11:08am
Test getDataStoreGroupList service on actual robot. |  |  | No command line arguments required | In third terminal window, it should display the list of groups in the DataStore | GetDataStoreGroupList: ...............................................................................................................................................(list of groups in the DataStore) EndOfGetDataStoreGroupList | passed on 4 dec 11:10am
Test getDataStoreGroupValues service on actual robot. |  |  | system | In third terminal window, it should display the values of a group in the DataStore | GetDataStoreGroupValues: RobotIP 168.3.201.122 GetDataStoreGroupValues: Odometer(KM) 16 GetDataStoreGroupValues: OdometerKM_MM 16 km, 239648.062 mm GetDataStoreGroupValues: HourMeter 679 GetDataStoreGroupValues: Idle 0 EndOfGetDataStoreGroupValues | passed on 4 dec 11:12am
Test getDataStoreTripGroupList service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should display the list of groups in the DataStore that contain trip information | GetDataStoreTripGroupList: LastTripReset GetDataStoreTripGroupList: TripJobCounts GetDataStoreTripGroupList: TripStateInformation EndOfGetDataStoreTripGroupList | passed on 4 dec 11:19am
Test getGoals service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should return a list of goal names found in the current map | Goal: Goal3 Goal: Goal1 Goal: Goal2 End of goals | passed on 4 dec 11:21am
Test getInfoList service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should return the list of information names | InfoList: RobotIP InfoList: WirelessLink InfoList: WirelessQuality InfoList: Local Plan Time InfoList: Local DWA Time InfoList: Num New Obstacle Points InfoList: Closest Obs Distance InfoList: PlanTime Limited Lin Vel InfoList: Local Plan Area Size X InfoList: Local Plan Area Size Y InfoList: Odometer(KM) InfoList: HourMeter InfoList: Temperature(C) InfoList: LaserScore InfoList: LaserLock InfoList: LaserNumSamples InfoList: LaserNumPeaks InfoList: ChargeEstimate InfoList: CurrentDraw InfoList: PackVoltage InfoList: BatteryStatus InfoList: BatteryError InfoList: OnCharger InfoList: ChargeState InfoList: MPacs InfoList: Laser_1 Pacs InfoList: Laser_1 Filtered_v2 InfoList: SBC Uptime InfoList: ARAM Uptime InfoList: Idle InfoList: TipAngle InfoList: IsTipped InfoList: Queue ID InfoList: Queue Job ID InfoList: DebugLogState InfoList: DebugLogSeconds End of info list | passed on 4 dec 11:23am
Test getMacros service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should display a list of macros found in the current map | End of macros | passed on 4 dec 11:24am
Test getRoutes service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should display the list of route names found on the current map | Routes Route: Route1 End of routes | passed on 4 dec 1:33pm
Test help service on actual robot. |  |  | no cmd line arg required | In third terminal window, a list and brief description of available ARCL commands should be provided | switchableForbiddenList Gets the list and state of switchable forbiddens [sfL] switchForbiddenOff Switch a specific switchable forbidden off [sfOff] switchForbiddenOn Switch a specific switchable forbidden on [sfOn] switchForbiddensOffByPrefix Switch off switchable forbiddens by prefix [sfOffP] switchForbiddensOnByPrefix Switch on switchable forbiddens by prefix [sfOnP] tripReset Resets the trip values in the Data Store [tr] undock Undocks the robot (done automatically too) updateInfo updates a piece of information waitTaskCancel Cancels the wait task (if it's active, causing it to succeed) waitTaskFail Fails the wait task (if it's active) waitTaskState Gets the state of the wait task End of commands | passed on 4 dec 1:37pm
Test inputList service on actual robot. |  |  | no cmd line arg required | In third terminal window, the named digital inputs should be listed | InputList: i1 InputList: i10 InputList: i11 InputList: i12 InputList: i13 InputList: i14 InputList: i15 InputList: i16 InputList: i2 InputList: i3 InputList: i4 InputList: i5 InputList: i6 InputList: i7 InputList: i8 InputList: i9 End of InputList | passed on 4 dec 1:39pm
Test inputQuery service on actual robot. |  |  | i1 | In third terminal window, it should show the state of a named input | Input: i1 off | passed on 4 dec 1:41pm
Test log service on actual robot. |  |  | test | In third terminal window, it should show that the message to the normal log file has been logged | Logging 'test' with level Normal | passed on 4 dec 1:45pm
Test mapObjectInfo service on actual robot. |  |  | goal1 | In third terminal window, the information about a named map object should be shown | MapObjectInfo: "Goal1" Goal "" MapObjectInfoCoord: "Goal1" -770 23820 88.300 End of MapObjectInfo | passed on 4 dec 2:21pm
Test mapObjectList service on actual robot. |  |  |  | In third terminal window, the names of map objects of a given type should be shown
Test mapObjectTypeInfo service on actual robot. |  |  | door | In third terminal window, it should show the detailed information about a particular type of map object | MapObjectTypeInfoArgument: SecondExit string Normal "Goal to which to drive to go through the door (this is optional, but is paired with SecondEnter)" MapObjectTypeInfoArgument: FailureMacro string Detailed "Macro to call if the robot fails to get through the door" MapObjectTypeInfoArgument: DoorOutput string Important "Name of the door output that sends the signals to open the door" MapObjectTypeInfoArgument: WaitTime int Normal "Time to wait for door to open after sending the signal to open it" MapObjectTypeInfoArgument: SwingSector string Important "Sector that describes the swing of the door, this should include the door jam itself. When a robot has left this area, it will release the door." End of MapObjectTypeInfo | passed on 4 dec 1:58pm
Test mapObjectTypeList service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should show a list of the types of map objects in the map | MapObjectTypeList: DistanceAdjustment BoundaryType MapObjectTypeList: DistanceOneWay SectorType MapObjectTypeList: DistanceUncrossable BoundaryType MapObjectTypeList: Door SectorType MapObjectTypeList: DoorGoal GoalType MapObjectTypeList: DoorSwingSector SectorType MapObjectTypeList: DoorVirtual SectorType MapObjectTypeList: DriveOnRightSector SectorType MapObjectTypeList: FastSector SectorType MapObjectTypeList: Goal GoalType MapObjectTypeList: IgnoreDynamicObstacleSector SectorType MapObjectTypeList: IgnoreLowLaserSector SectorType MapObjectTypeList: IgnoreSonarSector SectorType MapObjectTypeList: IgnoreTiltedLaserSector SectorType MapObjectTypeList: ManagedDestination SectorType MapObjectTypeList: ManagedMotion SectorType MapObjectTypeList: ManagedMotionOverride SectorType MapObjectTypeList: Measure BoundaryType MapObjectTypeList: MovementParametersSector SectorType MapObjectTypeList: NeedToEnterSector SectorType MapObjectTypeList: NoLostSector SectorType MapObjectTypeList: OneWaySector SectorType MapObjectTypeList: OneWayTwoSidedLeftSector SectorType MapObjectTypeList: OneWayTwoSidedRightSector SectorType MapObjectTypeList: PathPlanningSettingsSector SectorType MapObjectTypeList: PreferredLine BoundaryType MapObjectTypeList: ResistedLine BoundaryType MapObjectTypeList: ResistedSector SectorType MapObjectTypeList: SlowSector SectorType MapObjectTypeList: StandbyGoal GoalType MapObjectTypeList: SwitchableForbiddenArea SectorType MapObjectTypeList: SwitchableForbiddenLine BoundaryType MapObjectTypeList: TaskSector SectorType MapObjectTypeList: TwoWayDriveOnLeftSector SectorType MapObjectTypeList: TwoWayDriveOnRightSector SectorType MapObjectTypeList: VeryFastSector SectorType MapObjectTypeList: VerySlowSector SectorType MapObjectTypeList: VolumeAdjustmentSector SectorType End of MapObjectTypeList | passed on 4 dec 2:00pm
Test newConfigParam service on actual robot. |  |  | section name description Basic string 10 1 1 test | In third terminal window, it should show that a custom parameter to ARAM’s configuration has been added | Will add new param 'name' to section 'section' | passed on 4 dec 2:03pm
Test newConfigSectionComment service on actual robot. |  |  | test1 test | In third terminal window, it should show that a comment has been added to a section | Will add config comment 'test' to section 'test1' | passed on 4 dec 2:10pm
Test odometerReset service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should show that the robot trip odometer has been reset | Reset odometer | passed on 4 dec 2:12pm
Test outputList service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should list the named digital outputs | OutputList: o1 OutputList: o10 OutputList: o11 OutputList: o12 OutputList: o13 OutputList: o14 OutputList: o15 OutputList: o16 OutputList: o2 OutputList: o3 OutputList: o4 OutputList: o5 OutputList: o6 OutputList: o7 OutputList: o8 OutputList: o9 End of OutputList | passed on 4 dec 2:15pm
Test outputOff service on actual robot. |  |  | o1 | In third terminal window, it should turn off the named digital output | Output: o1 off | passed on 4 dec 2:17pm
Test outputOn service on actual robot. |  |  | o1 | In third terminal window, it should turn on the named digital output | Output: o1 on | passed on 4 dec 2:18pm
Test outputQuery service on actual robot. |  |  | o1 | In third terminal window, it should show the state of a named output | Output: o1 on | passed on 4 dec 2:23pm
Test payloadQueryLocal service on actual robot. |  |  | cmd line arg optional | In third terminal window, it should query and show the payload for the robot and specified slot | EndPayloadQuery | passed on 4 dec 2:26pm
Test payloadRemove service on actual robot. |  |  |  | In third terminal window, it should the specified payload slot on the robot has been emptied |  | robot has no payload slots
Test payloadSet service on actual robot. |  |  |  | In third terminal window, it should that a payload slot on this robot has been defined |  | robot has no payload slots
Test payloadSlotCountLocal service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should display a slot count on the robot | PayloadSlotCount: "Robot122" 0 "" EndPayloadSlotCount | passed on 4 dec 2:39pm
Test popupSimple service on actual robot. |  |  | title message label 3 | In third terminal window, it should show that a popup message in the MobilePlanner software has been displayed | Creating simple popup | passed on 4 dec 2:43pm
Test queueCancelLocal service on actual robot. |  |  | status inprogress | In third terminal window, it should show that a queued request for a robot has been canceled | queuecancel attempting to cancel "status" "inprogress" "" "None" queuecancel cancelling "status" "inprogress" "" "None" from queue queuecancel has failed to cancel "status" "inprogress" "" "None" failure cause "no matching status found" QueueUpdate: PICKUP1 JOB1 10 Pending None Goal "goal1" "None" 12/05/2019 02:46:13 None None 0 | passed on 4 dec 2:46pm
Test queueDropoff service on actual robot. |  |  | goal1 | In third terminal window, it should show that Queues the robot to the dropoff goal | QueueUpdate: DROPOFF2 JOB2 20 Pending None Goal "goal1" "Robot122" 12/05/2019 02:54:36 None None 0 queuedropoff goal "goal1" with priority 20 id DROPOFF2 and job_id JOB2 successfully queued queuedropoff attempting to queue goal "goal1" using default priority | passed on 4 dec 2:55pm
Test queueModifyLocal service on actual robot. |  |  | DROPOFF5 goal goal1 | In third terminal window, it should show that a goal and priority for job segment has been modified | QueueUpdate: DROPOFF5 JOB5 20 BeforeModify None Goal "goal2" "Robot122" 12/05/2019 02:56:48 None None 0 QueueUpdate: DROPOFF5 JOB5 20 AfterModify None Goal "goal1" "Robot122" 12/05/2019 02:56:48 None None 0 QueueUpdate: DROPOFF5 JOB5 20 Pending None Goal "goal1" "Robot122" 12/05/2019 02:56:48 None None 0 queuemodify modifying id DROPOFF5 goal "goal1" | passed on 4 dec 3:00pm
Test queueQueryLocal service on actual robot. |  |  | status pending | In third terminal window, it should show the job status of the robot queue by type or value | QueueQuery: DROPOFF5 JOB5 20 Pending None Goal "goal1" "Robot122" 12/05/2019 02:56:48 None None "" 0 EndQueueQuery | passed on 4 dec 3:03pm
Test quit service on actual robot. |  |  | no cmd line arg required | In third terminal window, the connection to the server should be closed | closing connection | passed on 4 dec 3:05pm
Test say service on actual robot. |  |  | “hello” | In third terminal window, it should show that a text string through the robot audio output has been played | Saying hello | passed on 4 dec 3:07pm
Test shutdown service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should show that the robot is shutting down | Shutting down | passed on 4 dec 3:09pm
Test tripReset service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should show the trip values in the DataStore has been reset | tripReset: TripCancelledInProgressJobSegments 0 tripReset: TripFailedJobSegments 0 tripReset: TripInterruptedJobSegments 0 tripReset: TripDropOffDrivingTime 0.000 tripReset: TripDropOffDrivingDistance 0.000 tripReset: TripPickupDrivingTime 0.000 tripReset: TripPickupDrivingDistance 0.000 tripReset: TripParkingTime 0.000 tripReset: TripParkingDistance 0.000 tripReset: TripDockingTime 0.000 tripReset: TripDockingDistance 0.000 tripReset: TripForceDockingTime 0.000 tripReset: TripForceDockingDistance 0.000 tripReset: TripDockedTime 0.000 tripReset: TripForceDockedTime 0.000 tripReset: TripInFaultTime 0.000 tripReset: TripInEstopTime 0.000 tripReset: TripAfterTime 0.000 tripReset: TripParkedTime 0.000 tripReset: TripBufferedTime 0.000 tripReset: TripCompletedJobs 0 tripReset: TripCompletedJobSegments 0 tripReset: TripCancelledJobs 0 tripReset: TripCancelledJobSegments 0 tripReset: TripModifiedJobSegments 0 EndOfTripReset | passed on 4 dec 3:18pm
Test updateInfo service on actual robot. |  |  | Test 1 | In third terminal window, it should the value for an existing piece of information has been updated | Updated info for test | passed on 4 dec 3:20pm
Test waitTaskCancel service on actual robot. |  |  | no cmd line arg required | In third terminal window, it should show that a wait task is canceled if active | WaitState: Not waiting | passed on 4 dec 3:22pm
Test dock action on actual robot. | robot ip have to be Set when launching launch File as command line arg and action argument if required has to be set in action client file | 1. Open 3 terminal windows 2. In one terminal run command: “roscore” 3. In second terminal window, run command: roslaunch om_aiv_util test_roslaunch.launch ip:=168.3.201.122 (ip address is unique to each robot) 4. In third terminal windows, run command: rosrun om_aiv_navigation dock_action_client.py 5. repeat step 4 for other actions | no cmd line arg required | robot should move to the dock and get docked | Feedback received: received_data: "DockingState: Docked ForcedState: Unforced ChargeState: Overcharge\r\n" The result is: status: "ockingState: ,Docked ForcedState: Unforced ChargeState: Overcharge" | passed on 5dec 4:19am
Test dock action on actual robot. |  |  | Move 1000 | robot should perform a single task | Feedback received: received_data: "Will do task move 1000\r\n" The result is: status: "Completed doing task move 1000" | passed on 5 dec 10:27am
Test executeMacro action on actual robot. |  |  | macro1 | robot should execute the specific macro | Feedback received: received_data: "Executing macro macro1\r\n" Feedback received: received_data: "Executing macro macro1\r\nCompleted macro macro1\r\n" | passed on 5 dec 10:49am
Test patrol action on actual robot. |  |  | Route1 | robot should initiate continuous patrol of the named route | Feedback received: received_data: "Patrolling route Route1\r\n" Feedback received: received_data: "Patrolling route Route1\r\nInterrupted: Patrolling route Route1\r\n" Feedback received: received_data: "Patrolling route Route1\r\nInterrupted: Patrolling route Route1\r\nPatrolling route\ \ Route1\r\n" Feedback received: received_data: "Patrolling route Route1\r\nInterrupted: Patrolling route Route1\r\nPatrolling route\ \ Route1\r\nCompleted patrol, patroling again\r\n" | passed on 5 dec 10:57am
Test patrolOnce action on actual robot. |  |  | Route1 | Robot shoul patrol the named route one time | Feedback received: received_data: "Patrolling route Route1 once\r\n" The result is: status: "Finished patrolling route Route1" | passed on 5 dec 11:00am
Test patrolResume action on actual robot. |  |  | Route2 | Continue navigating the current route. | Feedback received: received_data: "Patrolling route Route1 once\r\nInterrupted: Patrolling route Route1 once\r\nStopping\r\ \nStopped\r\n" The result is: status: "Finished patrolling route Route1" | passed on 5 dec 11:02am
Test play action on actual robot. |  |  | 0000.wav | Robot should play a .wav sound file | Feedback received: received_data: "Playing 0000.wav\r\n" The result is: status: "Playing 0000.wav" | passed on 5 dec 11:18am
Test stop action on actual robot. |  |  | no arg required | The current robot motion should be stopped | Feedback received: received_data: "Interrupted: Patrolling route Route1 once\r\n" The result is: status: "Stopped" | passed on 5 dec 11:28am
Test queueDropoff action on actual robot. |  |  | goal1 | Queues the robot to the dropoff goal and robot should move to goal spcified | Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nqueuedropoff goal \"goal1\" with\ \ priority 20 id DROPOFF1 and job_id JOB1 successfully queued\r\n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nqueuedropoff goal \"goal1\" with\ \ priority 20 id DROPOFF1 and job_id JOB1 successfully queued\r\nGoing to goal1\r\ \n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nqueuedropoff goal \"goal1\" with\ \ priority 20 id DROPOFF1 and job_id JOB1 successfully queued\r\nGoing to goal1\r\ \nQueueUpdate: DROPOFF1 JOB1 20 InProgress Allocated Goal \"goal1\" \"Robot122\"\ \ 12/05/2019 23:32:06 None None 0 \r\n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nqueuedropoff goal \"goal1\" with\ \ priority 20 id DROPOFF1 and job_id JOB1 successfully queued\r\nGoing to goal1\r\ \nQueueUpdate: DROPOFF1 JOB1 20 InProgress Allocated Goal \"goal1\" \"Robot122\"\ \ 12/05/2019 23:32:06 None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress Driving\ \ Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nqueuedropoff goal \"goal1\" with\ \ priority 20 id DROPOFF1 and job_id JOB1 successfully queued\r\nGoing to goal1\r\ \nQueueUpdate: DROPOFF1 JOB1 20 InProgress Allocated Goal \"goal1\" \"Robot122\"\ \ 12/05/2019 23:32:06 None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress Driving\ \ Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nArrived at goal1\r\ \n" Feedback received: received_data: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nqueuedropoff goal \"goal1\" with\ \ priority 20 id DROPOFF1 and job_id JOB1 successfully queued\r\nGoing to goal1\r\ \nQueueUpdate: DROPOFF1 JOB1 20 InProgress Allocated Goal \"goal1\" \"Robot122\"\ \ 12/05/2019 23:32:06 None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress Driving\ \ Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nArrived at goal1\r\ \nQueueUpdate: DROPOFF1 JOB1 20 Completed None Goal \"goal1\" \"Robot122\" 12/05/2019\ \ 23:32:06 12/05/2019 23:32:19 0 \r\n" The result is: status: "queuedropoff attempting to queue goal \"goal1\" using default priority\r\nQueueUpdate:\ \ DROPOFF1 JOB1 20 Pending None Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06\ \ None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress UnAllocated Goal \"goal1\"\ \ \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nqueuedropoff goal \"goal1\" with\ \ priority 20 id DROPOFF1 and job_id JOB1 successfully queued\r\nGoing to goal1\r\ \nQueueUpdate: DROPOFF1 JOB1 20 InProgress Allocated Goal \"goal1\" \"Robot122\"\ \ 12/05/2019 23:32:06 None None 0 \r\nQueueUpdate: DROPOFF1 JOB1 20 InProgress Driving\ \ Goal \"goal1\" \"Robot122\" 12/05/2019 23:32:06 None None 0 \r\nArrived at goal1\r\ \nQueueUpdate: DROPOFF1 JOB1 20 Completed None Goal \"goal1\" \"Robot122\" 12/05/2019\ \ 23:32:06 12/05/2019 23:32:19 0 \r\n" | passed on 5 dec 11:33am
Test undock action on actual robot. |  |  | no arg required | Robot should undock | Feedback received: received_data: "DockingState: Undocked ForcedState: Unforced ChargeState: Bulk\r\n" The result is: status: "DockingState: Undocked ForcedState: Unforced ChargeState: Bulk\r\n" | passed on 5 dec 11:53am
Able specify robot name and Ip address as command line args When runing launch file |  |  |  | Able to specify robot name and Ip address as Command line args When runing launch file
testplan
Actions – queuepickup drop off
firmware version | ARAM 4.9.27 | ARAM 5.0.12
have another file to pass arguments to launch file from txt file
timeout for rospy.waitforservice
Readme – arcl doumentation
another package to have user client programs to call server programs
1. Dont need so many servers
2. Dynamic service srv file – just one
3. ld_status_publisher init node once can already
4. rate.sleep – remove from files – use rosTime – ld publisher
5. use rospy.spin dont need loop forever – ld publisher
6. make package compatible with future/newer ros versions

## getInfo
InfoList: WirelessLink
InfoList: WirelessQuality
InfoList: Odometer(KM)
InfoList: HourMeter
InfoList: Temperature(C)
InfoList: LaserScore
InfoList: LaserLock
InfoList: LaserNumSamples
InfoList: LaserNumPeaks
InfoList: MPacs
InfoList: Laser_1 Pacs
InfoList: SBC Uptime
InfoList: ARAM Uptime
InfoList: Idle
InfoList: TipAngle
InfoList: IsTipped
InfoList: Queue ID
InfoList: Queue Job ID
InfoList: DebugLogState
InfoList: DebugLogSeconds

## block diagram
ROS Launch File for Actions
om_aiv_package
om_aiv_navigation
package
ROS Launch File for
Services and Topics
LD_ROS
workspace
Action servers (waiting for
client/s)
Action client/s (send command
to client)
waiting
Action server file/s sends command
To ARCL
Topics published
Service servers (waiting for client)
Rostopic echo
Subscribes to
topic/s
Service client/s (send command
to client)
waiting
Service server file/s sends command
To ARCL
Get back response
And required data
Robot executes
command/s.
Get back response/s

## Sheet6
convert queuedrop off to action
Action client can be implemented in user program
test plan and doumentation